GOMOA WEST DISTRICT ASSEMBLY

DPCU

COMPOSITE ANNUAL ACTION PLAN - 2025

# TABLE OF CONTENTS

Contents

TABLE OF CONTENTS	i

BRIEF PROFILE	1

List of Development Issues	3

Social	3

Social protection	3

Business Development	3

Infrastructure	3

Natural Resource Endowment	3

Environment	3

2025 AAP MATRIX	4

# BRIEF PROFILE

L.I. 1896 created Gomoa West from Gomoa District with its capital as Apam in July, 2008. It shares boundaries to the North with Asikuma–Odoben- Brakwa District and Agona West Municipal Assemblies, on the South by the Atlantic Ocean, to the East and East by Gomoa East District and Effutu Municipality respectively, and on West by Ajumako-Enyan-Essiam and Ekumfi Districts respectively. The district covers a land area of 514.2 square kilometers.

Figure 1 : CHPS Compound Map

## List of Development Issues

### Social

#### Education

- Inadequate furniture for pupils and teachers.

- Dilapidated classroom blocks.

- Insufficient teaching and learning materials.

- Inadequate accommodation for teachers in the District

- High level of teacher attrition

#### Health

- Inadequate medical logistics.

- Dilapidated health facilities.

- Inadequate accommodation for health professionals in the District.

- Inadequate medical staff

### Social protection

#### Poverty

- About 22.6% of household population live below the poverty line.

#### Child Poverty

- The District has about 28,000 children in poor households.

#### Persons Living with Disability

- About 6,400 PWDs not registered with the District Assembly for intervention.

### Business Development

#### Fishing

- Inadequate storage facilities for fisher folks and farmers.

- Poor conditions of landing sites in the District.

#### Job creation

- About 7,000 persons in the District are unemployed.

#### Markets

- Poor condition of major markets.

### Infrastructure

#### Transportation network

- 150km of feeder roads in the District are unmotorable.

- Potholes on roads.

#### Water

- 33% of households not having access to potable water.

### Natural Resource Endowment

#### Tourism

- Undeveloped tourist potentials.

#### Land pollution

- Existence of open defecation in all communities.

- About 60% of solid waste not managed properly.

### Environment

- Evidence of climate change in the District.

# 2025 AAP MATRIX

| S/N | PROGRAMS | SUB-PROGRAMS | LIST OF PROJECTS | LOCATION | OUTPUT INDICATOR | TIME FRAME |  |  |  | INDICATIVE BUDGET (GH¢) |  |  |  |  | IMPLEMENTING AGENCY |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 1 | 2 | 3 | 4 | IGF | GOG | DACF | DACF RFG | DONOR | LEAD | COLLA |
|  | MANAGEMENT AND ADMINISTRATION | General Administration | Support Internal Management of Organization | District Assembly | Internal managerial activities supported | X | X | X | X | 503,470.90 |  | 459,549.13 |  |  | GWDA | CAD |
|  |  |  | Protocol Service |  |  |  |  |  |  | 3,000.00 |  |  |  |  |  |  |
|  |  |  | Support Operations of Security Services | District wide | Security Operations improved | X | X | X | X | 10,000.00 |  | 9,925.56 |  |  | GWDA | GPS / GNFS / GIS |
|  |  |  | Encourage Citizen Participation in Local Governance (Community Engagement) | District wide | Citizen participation improved | X | X | X | X | 16,000.00 |  | 57,368.18 |  |  | GWDA | CAD |
|  |  |  | Strengthen Local and International Affiliations | District wide | Local and International bonds strengthened | X | X | X | X | 2,000.00 |  | 20,000.00 |  |  | GWDA | CAD |
|  |  |  | Organize Official Celebrations (May Day) | District wide | No. of Celebrations organized | X | X | X | X | 20,000.00 |  | 10,000.00 |  |  | GWDA | CAD |
|  |  |  | Support Traditional Authorities | District wide | Traditional Authorities supported | X | X | X | X | 10,000.00 |  | 30,000.00 |  |  | GWDA | CAD |
|  |  |  | Procure Office Equipment and Logistics | Apam | Office Equipment procured | X | X | X | X | 50,000.00 |  | 30,000.00 |  |  | GWDA | CAD |
|  |  |  | Undertake payment of IGF Staff Salaries | Apam | IGF Staff Salaries paid | X | X | X | X | 155,145.48 |  |  |  |  | GWDA | CAD |
|  |  |  | Undertake payment of Transfer Grants | District wide | Transfer Grants paid | X | X | X | X | 23,323.62 |  |  |  |  | GWDA | CAD |
|  |  | Finance and Audit | FINANCE AND ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Undertake Revenue Mobilization and Improvement exercises | District Assembly | Revenue mobilization improved | X | X | X | X | 83,000.00 |  |  |  |  | GWDA | CAD, DFD |
|  |  |  | Support Internal Audit Operations | Apam | Audit operations supported | X | X | X | X | 12,000.00 |  | 6,000.00 |  |  | GWDA | CAD, IAU |
|  |  |  | Treasury and Accounting Activities | District wide | Accounting activities supported | X | X | X | X | 59,000.00 |  | 5,000.00 |  |  | GWDA | CAD, DFD |
|  |  |  | Audit Committee Meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Human Resource Management | Undertake Staff Training and Skills Development | Apam | No. of trainings undertaken | X | X | X | X | 8,000.00 |  | 10,000.00 | 30,000.00 |  | GWDA | HRMD |
|  |  |  | PLANNING, BUDGETING, COORDINATING AND STATISTICS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Support Administrative Expenses | Apam | Administrative Expenses supported | X | X | X | X |  | 8,000.00 |  |  |  | GWDA | HRMD |
|  |  |  | Undertake Plans and Budget preparation | Apam | Plans and Budget prepared | X | X | X | X | 33,000.00 |  | 93,844.03 |  |  | GWDA | DPU, BU |
|  |  |  | Embark on Data Collection activities | District wide | Data Collected | X | X | X | X | 5,000.00 |  |  |  |  | GWDA | STATS |
|  |  |  | Conduct regular Monitoring and Evaluation of Programs | District wide | M&E Exercises conducted | X | X | X | X | 4,000.00 |  |  |  |  | GWDA | CAD |
|  |  |  | Undertake Climate Change ResponsiveActivities | District wide | Climate Change Responsive activities undertaken | X | X | X | X |  |  | 4,000.00 |  |  | GWDA | Planning, Parks & Gar. |
|  |  |  | Support Sub Structures Activities | Sub-district offices | No. of sub-structure activities supported | X | X | X | X |  |  | 110,000.00 |  |  | GWDA | CAD |
|  |  |  | Undertake Climate Change and Green Economy related activities | District wide | No. of activities undertaken | X | X | X | X | 5,000.00 |  | 19,925.56 |  |  | GWDA | DPCU |
|  |  |  | Support Legal Activities | District wide | No. of activities supported | X | X | X | X | 5,000.00 |  |  |  |  | GWDA | CAD |
|  |  |  | HUMAN RESOURCE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Undertake Salary Validation | Apam | No. of Staff validated | X | X | X | X | 3,000.00 |  |  |  |  | GWDA | HRMD |
|  |  |  | Undertake Monitoring and Supervision of IGF Staff | Apam | IGF Staff monitored | X | X | X | X | 2,000.00 |  |  |  |  | GWDA | HRMD |
|  |  |  | Personnel and Staff | Apam |  |  |  |  |  | 1,200.00 |  |  |  |  |  |  |
|  |  |  | Staff training and skills development |  |  |  |  |  |  | 8,000.00 | 10,000.00 | 30,000.00 |  |  |  |  |
|  |  |  | Organize Occupational Health and Safety programs | Apam | No. of programs organized | X | X | X | X |  |  | 10,000.00 |  |  | GWDA | HRMD |
|  |  |  | EDUCATION, YOUTH AND SPORTS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SOCIAL SERVICES DELIVERY | Education, Youth and Sport Services | Provide support to Teaching and Learning activities | District wide | Teaching and Learning supported | X | X | X | X | 5,000.00 |  | 226,594.40 |  |  | GWDA | DED |
|  |  |  | Organize Official Celebration (6th March) |  | Official Celebration organized | X | X | X | X |  |  | 30,000.00 |  |  | GWDA | DWD, DED |
|  |  |  | Promote the development of Youth through Sports and Culture | District wide | No. of activities undertaken | X | X | X | X | 2,000.00 |  | 77,729.60 |  |  | GWDA | DED, CO |
|  |  |  | Complete 1 No. 3-Unit classroom block | Gomoa Obiri | 1no.3-unit Classroom Block completed | X | X | X | X |  |  | 98,718.61 |  |  | GWDA | DED, DWD |
|  |  |  | Complete 1no. 6-unit Teachers’ Quarters | Gomoa Mankoadze | 1no. 6-unit Teachers' Quarters completed | X | X | X | X |  |  |  | 460,723.35 |  | GWDA | DWD, DED |
|  |  |  | Complete 1no. 3-unit classroom block | Gomoa Appiakrom-Debiso | 1no. 3-unit Classroom Block completed | X | X | X | X |  |  | 226,951.66 |  |  | GWDA | DWD, DED |
|  |  |  | Complete 1no. 2-unit KG block | Gomoa Antseadze | 1no. 2-unit KG Block completed | X | X | X | X |  |  | 24,000.00 |  |  | GWDA | DWD, DED |
|  |  |  | Complete 1no. 3-unit Teachers’ Quarters | Gomoa Brofo | 1no. 3-unit Teachers’ Quarters completed | X | X | X | X |  |  | 4,970.80 |  |  | GWDA | DWD, DED |
|  |  |  | Complete 1no. 3-unit Teachers’ Quarters | Gomoa Darmang | 1no. 6-unit Teachers’ Quarters completed | X | X | X | X |  |  | 6,835.43 |  |  | GWDA | DED, DWD |
|  |  |  | Complete 1no. 6-unit Teachers' Quarters | Apam | 1no. 6-unit Teachers' Quarters completed | X | X | X | X |  |  |  | 415,863.90 |  | GWDA | DWD, DED |
|  |  |  | PUBLIC HEALTH SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Public Health Services and Management | Support Campaign towards Malaria prevention | District wide | Reported cases of Malaria reduced by 0.5% | X | X | X | X |  |  | 15,599.04 |  |  | GWDA | DHD |
|  |  |  | Embark on Public Health related activities | District wide | No. of embarked | X | X | X | X | 2,000.00 |  |  |  |  | GWDA | DHD |
|  |  |  | Support Medical Screening activities (Breast Screening Exercises) | District wide | No. of Screening Exercises supported | X | X | X | X | 3,0000.00 |  |  |  |  | GWDA | DHD |
|  |  |  | Support HIV/AIDS related activities | District wide | No. of activities supported | X | X | X | X |  |  | 5,380.00 |  |  | GWDA | DHD |
|  |  |  | Construct 1no. CHPS Compound | Apam - Nsuekyir | 1no. CHPS Compound constructed | X | X | X | X |  |  |  |  |  | GWDA | DHD, DWD |
|  |  |  | Construct 1no. CHPS Compound | Gomoa Mampong | 1no. CHPS Compound constructed | X | X | X | X |  |  |  | 500,000.00 |  | GWDA | DHD, DWD |
|  |  |  | Complete 1no. Clinic with Nurses Quarters | Gomoa Eshiem | 1no. Clinic with Nurses Quarters completed | X | X | X | X |  |  | 21,602.02 |  |  | GWDA | DWD, DHD |
|  |  |  | SOCIAL WELFARE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Social Welfare and Community Development | Support Internal Management of the Organization | District Assembly | Internal Management activities supported | X | X | X | X | 8,000.00 |  |  |  |  | GWDA | SWCD |
|  |  |  | Support Administrative Expenses | District Assembly | Administrative Expenses supported | X | X | X | X |  | 2,800.00 |  |  |  | GWDA | SWCD |
|  |  |  | Undertake Child Protection activities (ISSD) | District wide | No. of Child Protection activities undertaken | X | X | X | X |  |  |  | 30,000.00 |  | GWDA | SWCD, NGO |
|  |  |  | Combat Domestic Violence and Human Trafficking | District wide | No. of interventions undertaken | X | X | X | X | 3,000.00 |  |  |  |  | GWDA | SWCD, NGO |
|  |  |  | Organize Public Education campaign on Child Delinquency | District wide | No. of campaigns organized | X | X | X | X | 2,000.00 |  | 2,150.00 |  |  | GWDA | SWCD |
|  |  |  | Mainstream Gender Empowerment activities | District wide | No. of activities undertaken | X | X | X | X | 2,500.00 |  |  |  |  | GWDA | GDO, CAD / SWCD |
|  |  |  | Support PWD, women and vulnerable- promote registration and rehabilitation | District wide | No. of vulnerable supported | X | X | X | X |  |  | 203,026.24 |  |  | GWDA | SWCD |
|  |  | Birth and Death Registration Services | Promote Registration of Infants at birth | District wide | No. of public educations organized | X | X | X | X | 8,760.00 |  |  |  |  | GWDA | B&D |
|  |  |  | Support General Expenses | Apam | Expenses supported | X | X | X | X | 2,000.00 |  |  |  |  | GWDA | B&D |
|  |  |  | Organize Public Education on Birth and Death Registration | District wide | No. of campaigns undertaken | X | X | X | X | 2,400.00 |  |  |  |  | GWDA | B&D |
|  |  | Environmental Health and Sanitation Services | Construct 1no. Stray Animal Pound | District Assembly | 1no. Animal Pound constructed | X | X | X | X |  |  | 60,000.00 |  |  | GWDA | DWD, EHSU |
|  |  |  | ENVIRONMENTAL HEALTH |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Gazette District Assembly Bye-Laws |  | Bye-Laws gazetted | X | X | X | X |  |  | 8,000.00 |  |  | GWDA | CAD, EHSU |
|  |  |  | Organize Community Clean-Up Exercises | District wide | No. of Clean-Up Exercises organized | X | X | X | X | 8,000.00 |  | 20,000.00 |  |  | GWDA | EHSU |
|  |  |  | Manage Refuse Disposal Site | Gomoa Hwida | Refuse Disposal Site managed | X | X | X | X |  |  | 13,000.00 |  |  | GWDA | EHSU |
|  |  |  | Undertake Medical and Food Screening Exercises | District wide | No. of Screening Exercises undertaken | X | X | X | X | 5,500.00 |  |  |  |  | GWDA | EHSU |
|  |  |  | Undertake Sanitary Inspection and Compliance Enforcement | District wide | Sanitary conditions inspected and compliance enforced | X | X | X | X | 1,500.00 |  |  |  |  | GWDA | EHSU |
|  |  |  | Evacuate Refuse | District wide | Heaps of Refuse evacuated | X | X | X | X |  |  | 53,109.51 |  |  | GWDA | EHSU |
|  |  |  | Undertake Burial of Pauper | District wide | Pauper buried | X | X | X | X | 22,000.00 |  |  |  |  | GWDA | EHSU |
|  |  |  | Promote CLTS Campaign | District wide | No. of household latrines increased | X | X | X | X | 1,500.00 |  |  |  |  | GWDA | EHSU |
|  |  |  | Maintain Final Disposal Site | Gomoa Hwida | Final disposal site maintained | X | X | X | X |  |  | 13,000.00 |  |  | GWDA | EHSU |
|  |  |  | Undertake Solid Waste Management (SIP) | District wide | Solid Waste properly managed | X | X | X | X |  |  | 142,808.90 |  |  | GWDA | EHS, ZOOMLION |
|  |  |  | Undertake Liquid Waste Management (Fumigation) | District wide | Liquid waste management undertaken | X | X | X | X |  |  | 74,901.12 |  |  | GWDA | EHS, ZOOMLION |
|  |  |  | Support Internal Management of the Organization | District Assembly | Internal Management activities supported | X | X | X | X | 6,000.00 |  |  |  |  | GWDA | EHSU |
|  |  |  | Organize Spatial Planning meetings | Apam | No. of meetings organized | X | X | X | X | 10,560.00 |  |  |  |  | GWDA | PPD |
|  |  |  | Support Administrative Expenses | District Assembly | Administrative Expenses supported | X | X | X | X |  | 15,000.00 |  |  |  | GWDA | PPD |
|  |  |  | Undertake Street Naming and Property Addressing | Apam | No. of Streets signage installed and Properties addressed | X | X | X | X |  |  | 10,000.00 |  |  | GWDA | PPD |
|  |  |  | Register Assembly Land | District wide | Assembly Lands registered | X | X | X | X |  |  | 5,000.00 |  |  | GWDA | PPD |
|  |  |  | Ensure effective Land Use and Spatial Planning | District wide | LUSP regulations enforced | X | X | X | X |  |  | 10,000.00 |  |  | GWDA | PPD |
|  |  | PUBLIC WORKS, RURAL HOUSING AND WATER MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Undertake Monitoring and Evaluation of Programs and Projects | District wide | No. of M&E exercises conducted | X | X | X | X | 25,000.00 |  | 40,000.00 |  |  | GWDA | CAD, DWD |
|  |  |  | Renovate Residential Buildings | District Assembly | Assembly Buildings renovated | X | X | X | X | 9,000.00 |  | 225,500.00 |  |  | GWDA | DWD |
|  |  |  | Renovate Office Building | District Assembly | Office Building renovated | X | X | X | X | 13,640.00 |  | 140,000.00 |  |  | GWDA | DWD, CAD |
|  |  |  | Repair and maintain Roads | District wide | km of roads reshaped | X | X | X | X |  |  | 400,000.00 |  |  | GWDA | DWD |
|  |  |  | Undertake reshaping of Roads (MP) | District wide | km of roads reshaped | X | X | X | X |  |  | 57,729.60 |  |  | GWDA | MP'S OFFICE, DWD |
|  |  |  | Undertake Renovation of Markets (MP) | District wide | No. of markets renovated | X | X | X | X |  |  | 57,729.60 |  |  | GWDA | MP, DWD |
|  |  |  | Procure and install Street Lights | District wide | No. of Streetlights installed | X | X | X | X | 140,000.00 |  | 50,000.00 |  |  | GWDA | AREA COUNCILS |
|  |  |  | Embark on Road Safety Campaigns | District wide | No. of Campaigns undertaken | X | X | X | X |  |  |  |  |  | GWDA | DWD, GPRTU |
|  |  |  | Support to Strengthen the sub structures |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Constructional Materials |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Procure and Supply Construction Materials for community-initiated projects (MP) | District wide | Construction materials supplied | X | X | X | X |  |  | 173,188.79 |  |  | GWDA | MP'S OFFICE, DWD |
|  |  |  | Donations |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Contributions |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Undertake Renovation of Market (IGF 20%) | Kyiren-Nkwanta | 1no. market renovated | X | X | X | X | 90,000.00 |  |  |  |  | GWDA | DWD |
|  |  |  | Undertake Renovation of Market Toilet (IGF 20%) | Gomoa Dawurampong | 1no. market toilet renovated | X | X | X | X | 90,000.00 |  |  |  |  | GWDA | DWD |
|  |  |  | Complete 1no. Area Council Office | Gomoa Dawurampong | 1no. Area Council Office completed | X | X | X | X |  |  | 9,091.90 |  |  | GWDA | DWD |
|  |  |  | Development of Website |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Install and Maintain Early Fire Warning Systems | District Assembly | Systems installed and maintained | X | X | X | X |  |  | 6,000.00 |  |  | GWDA | DWD |
|  |  |  | Construct 1no. 2-unit Staff Quarters | Apam | 1no. 2-unit Staff Quarters constructed | X | X | X | X |  |  | 650,000.00 |  |  | GWDA | DWD |
|  |  |  | Support Self Help Projects | District wide | No. of Community Projects supported | X | X | X | X |  |  | 200,000.00 |  |  | GWDA | CAD |
|  |  |  | TRADE, TOURISM AND INDUSTRY |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Promote Local Economic Development | District wide | LED activities promoted | X | X | X | X | 3,000.00 |  | 98,420.46 |  |  | GWDA | DPU, BAC |
|  |  |  | Promote Trade Development | District wide | No. of activities organized | X | X | X | X | 4,000.00 |  |  |  |  | GWDA | BAC |
|  |  |  | Organize Community Based Trainings | District wide | No. of trainings organized | X | X | X | X | 2,000.00 |  |  |  |  | GWDA | BAC |
|  |  |  | Official Celebration |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Support Festival and other customary activities/Celebrations | District wide | Festivals celebrated | X | X | X | X |  |  | 15,342.05 |  |  | GWDA | CAD |
|  |  |  | Develop and manage Tourism potentials | District wide | No. of Tourism potentials developed and managed | X | X | X | X |  |  | 4,500.00 |  |  | GWDA | DPU, BAC |
|  |  |  | Participate in CENTRAL EXPO'24, Central Regional Investment and Trade Fair/conference | Cape Coast | Event participated |  |  | X |  |  |  | 30,000.00 |  |  | GWDA | BAC |
|  |  |  | Participate in Culture Activity (GAVA Fair) | District wide | Event participated | X | X | X | X |  |  | 12,000.00 |  |  | GWDA | CO |
|  |  | AGRIC SERVICES AND MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Agriculture | Support Administrative Expenses | District wide | Administrative Expenses | X | X | X | X |  | 25,000.00 |  |  |  | GWDA | DAD |
|  |  |  | Support Monitoring and Supervision activities | District wide | Monitoring and Supervision undertaken | X | X | X | X |  |  | 43,200.00 |  |  | GWDA | DAD |
|  |  |  | Implement Agriculture Extension Services | District wide | No. of farmers assigned AEAs | X | X | X | X |  |  | 6,000.00 |  |  | GWDA | DAD |
|  |  |  | Organize Official celebration (Farmers Day Celebration) | District wide | Farmers Day Celebration conducted | X | X | X | X |  |  | 223,594.40 |  |  | GWDA | DAD |
|  |  |  | Undertake Climate Change Interventions | District wide | Climate Change interventions undertaken | X | X | X | X |  |  | 9,000.00 |  |  | GWDA | DAD |
|  |  |  | Support implementation of Planting for Food and Jobs (PFJ) | District wide | PFJ implemented | X | X | X | X |  |  | 24,618.37 |  |  | GWDA | DAD |
|  |  |  | Support implementation of Mechanization for Food and Job (MFJ) | District wide | MFJ implemented | X | X | X | X |  |  | 25,526.47 |  |  | GWDA | DAD |
|  |  |  | Support implementation of Planting for Export and Rural Development (PERD) | District wide | PERD implemented | X | X | X | X |  |  | 12,000.00 |  |  | GWDA | DAD |
|  |  |  | Undertake Surveillance and Control of Pests and Livestock in the District | District wide | Post-harvest losses reduced by % | X | X | X | X |  |  | 6,000.00 |  |  | GWDA | DAD |
|  |  |  | DISASTER PREVENTION AND MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ENVIRONMENTAL MANAGEMENT | Disaster Prevention and Management | Support Disaster Management and Prevention in the District | District wide | Disaster occurrence reduced by 5% | X | X | X | X | 4,000.00 |  | 20,000.00 |  |  | GWDA | CAD, NADMO |
|  |  |  | Support Internal Management of the Organization | District Assembly | Internal Management supported | X | X | X | X | 6,000.00 |  |  |  |  | GWDA | NADMO |
|  |  |  | Climate Change |  |  |  |  |  |  | 2,000.00 | 19,925.56 |  |  |  |  |  |
|  |  |  | Green Economy Activities |  |  |  |  |  |  | 3,000.00 |  |  |  |  |  |  |
|  |  |  | Organize Official Celebration (IDDR) | District wide | Official Celebration organized | X | X | X | X | 1,000.00 |  |  |  |  | GWDA | NADMO |